Complete End-of-Hosting Checklist

This list is not exhaustive:

Agree and record the decision to end hosting, including reasons, proposed end date, and named leads on both sides for delivery.

Confirm the forum’s future structure (independent or new host) and record any required legal steps, timelines, and who is responsible.

Check grant conditions and notify funders early; obtain written consent before transferring any grant funds, responsibilities, or reporting arrangements.

Complete a final financial reconciliation: funds held for forum purposes, restricted funds, agreed support/overheads, and any outstanding commitments.

Agree what monitoring/reporting is due (mid-year or year-end) and schedule internal deadlines for drafting, review, and required sign-off. Talk to the grants team or your Contact adviser about your DfE grant.

Set up or confirm the forum’s bank account and finance processes (signatories, approvals, reconciliation routine) ahead of the exit date.

Create or update an asset/equipment register (owned vs loaned, condition, location) and agree item-by-item what transfers and what does not.

Agree how membership/supporter data and volunteer records will be transferred lawfully and transparently; document controller responsibilities and secure transfer method.

Transfer or recreate digital access before the exit date (domain, website, email accounts, cloud storage, shared drives, mailing platforms, admin rights, Multi Factor Authentication (MFA)). Agree a date for host access removal.

Agree ownership and permitted use of intellectual property (name, logo, branding, resources, training materials, website content, social media accounts/handles).

Review contracts and liabilities (suppliers, leases, insurance, staffing/TUPE considerations, complaints, disputes) and document what happens to each one.

Confirm key policies are in place and approved for the post-exit model (safeguarding, data protection, finance, complaints, decision-making, volunteer/staff policies).

Carry out a skills and capacity review of the steering group and agree gaps, training, mentoring, or temporary support to keep delivery safe and realistic.

Agree a communications plan and timeline for members, partners (local authority/ICB), funders, and volunteers, including a joint message and updated contact routes.

Put a written transition/exit agreement in place (end date, transfers, responsibilities, restricted funds, reporting, liabilities, and dispute resolution), signed by both parties.

Agree any post-exit support (what, by whom, how long, cost if any, and review date), and confirm what happens if issues arise after the split.